## Project
Total Project Tracking - Master Requirement & Feature Traceability Matrix
Full traceability mapping across 556 Git Commits, Controllers, API Endpoints, E2E Specs, Unit Tests, and NFR Specs.
# | Screen/Function | Feature Area | Actor | Screen/Function Description | In Charge | MSSV | Status | Iteration | Git Commit / PR Hash | Backend Controllers & API Routes | Frontend Stack & Components | Automated Tests (E2E & Unit) | NFR / Security / AI Audit | Complexity
1 | PostgreSQL Database Schema & Relational Model | Database & Architecture | System | Designed PostgreSQL relational schemas, JPA Entity models, indexes, transaction isolations, and DB seed scripts. | Nguyễn Văn Quang | DE190094 | Done | iter1 | init.sql, entity mappings | Database Schema, JPA Entities (User, Course, Problem, Contest, Transaction) | N/A (Database Core) | EntityUnitTest.java, DatabaseIntegrationTest.java | PostgreSQL 15, B-Tree Indexes, Referential Integrity, Isolation.REPEATABLE_READ | Critical
2 | Login Page | Authentication | User | Sign in using standard credentials or Google OAuth2 with secure HttpOnly cookies. | Võ Ngọc Thanh | DE190293 | Done | iter1 | 716d9e4, 85d5b38 | AuthenticationController, AuthenticationService (POST /api/v1/auth/login) | LoginPage.tsx, LoginForm.tsx, authStore.ts | AuthenticationServiceTest.java, auth-login.spec.ts | JWT Bearer Cookies, BCrypt (cost 12), Brute-force rate limit | Critical
3 | Register Page | Authentication | User | Sign up for student accounts and create initial profiles with email verification. | Võ Ngọc Thanh | DE190293 | Done | iter1 | 673d441, 716d9e4 | AuthenticationController, UserService (POST /api/v1/auth/register) | RegisterPage.tsx, RegisterForm.tsx | AuthenticationServiceTest.java, auth-register.spec.ts | Email Token Verification, Input XSS Sanitization | High
4 | User Profile Page | Profile | User | View/edit personal details, change passwords, avatar upload, and update emails. | Võ Ngọc Thanh | DE190293 | Done | iter1 | 63f1c99, 7c0afd4 | UserController, UserService (GET/PUT /api/v1/users/profile) | ProfilePage.tsx, AvatarUploader.tsx | UserServiceTest.java, student-profile.spec.ts | Cloudinary CDN Avatar Upload, Optimistic Locking (@Version) | Medium
5 | User Management Panel | Admin Dashboard | Admin | Admin interface to view users, search, and lock/unlock accounts dynamically. | Trịnh Hoàng Thiên Bảo | DE190023 | Done | iter1 | 76e9fa8, 0520a14 | AdminUserController, AdminDashboardService (GET/PATCH /api/v1/admin/users) | AdminUserTable.tsx, UserFilterBar.tsx | AdminDashboardServiceTest.java, admin-users.spec.ts | RBAC (@PreAuthorize('hasRole("ADMIN")')), Soft Delete, Dynamic JPA Specs | High
6 | Instructor Applications | Admin Dashboard | Admin | Review applicant CVs, check credentials, approve/reject with AI CV summary. | Trịnh Hoàng Thiên Bảo | DE190023 | Done | iter1 | 76e9fa8, c4c2b70 | InstructorApplicationController (POST /api/v1/admin/applications/{id}/approve) | ApplicantReviewModal.tsx, AISummaryBadge.tsx | InstructorApplicationServiceTest.java, instructor-approval.spec.ts | AI CV Summary (PDF Parsing + LLM), Async ApplicationApprovedEvent | High
7 | Problems Directory | Online Judge | User | View paginated list of public practice coding challenges with filters. | Võ Ngọc Thanh | DE190293 | Done | iter2 | 0a67378, 7c0afd4 | ProblemController, ProblemService (GET /api/v1/problems) | ProblemListPage.tsx, ProblemFilter.tsx | ProblemControllerTest.java, catalog-search.spec.ts | Redis Tag Caching, Full-Text Search Index, Prepared Statement SQL Protection | Medium
8 | Solve Problem Page | Online Judge | User | Integrated workspace to code solutions, run tests, and check results (Judge0). | Võ Ngọc Thanh | DE190293 | Done | iter2 | 998b82d, 4ce8206 | SubmissionController, Judge0Service (POST /api/v1/submissions) | ProblemSolvePage.tsx, MonacoEditor.tsx, TestResultPanel.tsx | Judge0ServiceTest.java, problem-solving.spec.ts | Docker Sandbox Execution via Judge0 API, Sub-second Polling, Memory/Time limits | Critical
9 | Course Directory | Course Learning | User | Browse and filter programming courses with a responsive grid layout. | Võ Ngọc Thanh | DE190293 | Done | iter2 | 74ba98a, 716d9e4 | CourseController, CourseService (GET /api/v1/courses) | CourseCatalogPage.tsx, CourseCard.tsx | CourseServiceTest.java, course-catalog.spec.ts | Responsive Grid, Dynamic Filtering, Lazy-loaded Image CDN | Medium
10 | Course Details | Course Learning | User | Deep view of course curriculum, chapters, video player, and student reviews. | Hồ Sĩ Tấn | DE190307 | Done | iter2 | 74ba98a, c4c2b70 | CourseController, CourseService (GET /api/v1/courses/{id}) | CourseDetailPage.tsx, VideoPlayer.tsx | CourseServiceTest.java, course-details.spec.ts | Cloudinary HLS Video Streaming, Enrolled Status Check, Safe Markdown Render | High
11 | Shopping Cart & Checkout | Course Learning | User | Add courses to cart, view wallet balance, and purchase courses safely. | Võ Ngọc Thanh | DE190293 | Done | iter2 | 283ca52, 12f8dc0 | PaymentController, PaymentService, WalletService (POST /api/v1/checkout) | CartPage.tsx, CheckoutModal.tsx | PaymentServiceTest.java, course-checkout.spec.ts | Idempotent Payments, Isolation.REPEATABLE_READ DB Transactions, Audit Logs | Critical
12 | Course Moderation | Admin Dashboard | Admin | AI-powered moderation checking course videos via FFmpeg transcriptions. | Trịnh Hoàng Thiên Bảo | DE190023 | Done | iter2 | c4c2b70, 76e9fa8 | CourseModerationController, CourseModerationService | ModerationQueuePage.tsx, VideoTranscriptViewer.tsx | CourseModerationServiceTest.java, course-moderation.spec.ts | FFmpeg Audio Extraction + Whisper AI Transcription + LLM Content Safety | Critical
13 | Instructor Revenue Analytics Dashboard | Instructor Dashboard | Instructor | Real database revenue analytics, lifetime gross/net calculations, 6/12-month timeframe toggles, dynamic SVG chart grid points. | Nguyễn Văn Quang | DE190094 | Done | iter2 | 6da05b2, 285bdb8, c4124a4 | InstructorRevenueController, RevenueService (GET /api/v1/instructor/revenue) | InstructorRevenueDashboard.tsx, RevenueChart.tsx | RevenueServiceTest.java, instructor-revenue.spec.ts | Realtime DB Revenue Aggregation, Zero-value Month Auto-padding, Dynamic SVG Grid | High
14 | Platform Financial Reports & Financial Metrics | Admin Dashboard | Admin | Platform-wide gross/net financial metrics, payout logs, transaction audit trail, optimized range queries. | Nguyễn Văn Quang | DE190094 | Done | iter2 | 3b2e60f, 33f57a6, 550369a | FinancialReportController, DashboardService (GET /api/v1/admin/reports) | FinancialDashboardPage.tsx, RevenueChart.tsx | DashboardServiceTest.java, financial-reports.spec.ts | Gross/Net Revenue Calculations, CSV Export, Indexed Range Queries | High
15 | Contest Directory & Spotlight Banner | Competitive Programming | User | View active/upcoming/ended contest list, status filter, dynamic spotlight banner, password registration lock. | Nguyễn Duy Phương | DE190416 | Done | iter2 | 12ad54d, e60d4c8, 0349342 | ContestController, ContestService (GET /api/v1/contests) | ContestListPage.tsx, SpotlightBanner.tsx, PasswordModal.tsx | ContestControllerTest.java, contest-arena.spec.ts | Password Locking (Argon2id), UTC ISO Time Synchronization, Registration Guard | High
16 | AI Tutor Panel | AI Assistance | User | Side panel in problem solver providing custom feedback and hint guidelines. | Võ Ngọc Thanh | DE190293 | Done | iter3 | 86bb8a8, 8644a3d | AiAssistanceController, AiEvaluationService (POST /api/v1/ai/tutor/hint) | AiTutorDrawer.tsx, HintBubble.tsx | AiEvaluationServiceTest.java, ai-tutor.spec.ts | Prompt Injection Shielding, Token Rate Limiting, Strict System Persona | High
17 | AI Algorithm Visualizer | AI Assistance | User | Visualizes code execution flows with adjustable speed and cached responses. | Võ Ngọc Thanh | DE190293 | Done | iter3 | 8644a3d, 85d5b38 | AiAssistanceController, AiEvaluationService (POST /api/v1/ai/visualize) | AlgorithmVisualizerCanvas.tsx, ExecutionSlider.tsx | AiEvaluationServiceTest.java, algorithm-visualizer.spec.ts | Redis Execution Trace Cache, Client-side Canvas Step Animation | High
18 | Lesson Q&A Comments | Course Learning | User | Ask questions under specific lessons and reply to other students. | Võ Ngọc Thanh | DE190293 | Done | iter3 | 74ba98a, 716d9e4 | CommentController, CommentService (POST /api/v1/lessons/{id}/comments) | LessonCommentSection.tsx, CommentThread.tsx | CourseServiceTest.java, lesson-comments.spec.ts | Tree Comment Hierarchy, Profanity Filter, Stored XSS Protection | Medium
19 | Create/Edit Course | Instructor Dashboard | Instructor | Create chapters, lectures, upload lecture videos to Cloudinary, and save drafts. | Hồ Sĩ Tấn | DE190307 | Done | iter3 | 046deeb, c4c2b70 | InstructorCourseController, InstructorCourseService (POST /api/v1/instructor/courses) | CourseBuilderPage.tsx, LectureUploader.tsx | InstructorCourseServiceTest.java, course-builder.spec.ts | Cloudinary Signed Upload Signatures, Draft Autosave, Cascading Soft Delete | Critical
20 | Monaco Code Editor Integration | Instructor Dashboard | Instructor | Integrated editor in coding exercises with syntax highlighting. | Hồ Sĩ Tấn | DE190307 | Done | iter3 | 998b82d, c4c2b70 | ExerciseController, InstructorCourseService | MonacoExerciseEditor.tsx, LanguageSelector.tsx | InstructorCourseServiceTest.java, monaco-editor.spec.ts | Multi-language Syntax (Java, C++, Python), Client Code Linting, Local Backup | High
21 | Auto Testcase Generator | Instructor Dashboard | Instructor | Auto-generate input/output testcases for instructor exercises. | Hồ Sĩ Tấn | DE190307 | Done | iter3 | c4c2b70, 8644a3d | TestcaseGeneratorController, AiEvaluationService | TestcaseGeneratorModal.tsx, InputOutputGrid.tsx | AiEvaluationServiceTest.java, testcase-generator.spec.ts | LLM Boundary Value Analysis, Edge Case Hardening, Docker Reference Exec | High
22 | Contest Arena Problem Workspace | Competitive Programming | User | Arena interface with live time countdown, anti-cheat mode (no hints), problem attempts persistence. | Nguyễn Duy Phương | DE190416 | Done | iter3 | 72086d9, de3576f, e69b5e7 | ContestController, ContestSubmissionRepository (POST /api/v1/contests/{id}/submissions) | ContestProblemSolve.tsx, MonacoEditor.tsx, ContestHeader.tsx | ContestControllerTest.java, problem-solving.spec.ts | Realtime WebSocket / SSE Feedback, Attempt History DB Persistence, Anti-cheat | Critical
23 | ICPC Live Scoreboard & Ranking Stream | Competitive Programming | User | Real-time ICPC penalty scoring engine (Redis ZSET + SSE Stream + JSON Snapshot DB Fallback Recovery). | Nguyễn Duy Phương | DE190416 | Done | iter3 | 774ca94, ca5496d, 7bc07b4, dfd2923 | ContestScoreboardController, RankingService (GET /api/v1/contests/{id}/stream) | LiveScoreboardPage.tsx, LeaderboardTable.tsx | ContestControllerTest.java, scoreboard.spec.ts | Redis Sorted Set (ZSET) Engine, SSE Live Stream, Snapshot JSON DB Fallback | Critical
24 | Dynamic Contest Status Evaluation Engine | Competitive Programming | System | Runtime evaluation of UPCOMING / ONGOING / ENDED states based on Instant.now(), eliminating static DB enum sync bugs. | Nguyễn Duy Phương | DE190416 | Done | iter3 | 2e3576f, 2c7ae5d, 8924b41, 9fab4b0 | ContestService, ContestRepository (JPQL Dynamic Queries) | ContestBadge.tsx, StatusFilterBar.tsx | ContestServiceTest.java, integration-tests.spec.ts | Zero DB Static Column Overhead, UTC Timestamp Precision, Dynamic Status JPQL | High
25 | Admin System Overview & Database Metrics | Admin Dashboard | Admin | Real-time DB health monitoring, total active user/course/submission counters, platform system statistics aggregation. | Nguyễn Văn Quang | DE190094 | Done | iter3 | 6b8b6f0, 536da33, 8d09c30 | AdminDashboardController, SystemMetricsService (GET /api/v1/admin/stats) | AdminDashboardPage.tsx, StatCard.tsx | DashboardServiceTest.java, admin-stats.spec.ts | Sub-second Query Execution, Cached Stat Aggregation (TTL 30s), DB Health Monitoring | Medium
26 | Admin Problem Management & Testcase Builder | Admin Dashboard | Admin | Comprehensive admin problem CRUD, input/output testcase builder, sample vs hidden testcase management. | Nguyễn Văn Quang | DE190094 | Done | iter3 | 9c39a98, 434df81, 0cf9d01 | AdminProblemController, TestcaseService (POST /api/v1/admin/problems) | AdminProblemEditor.tsx, TestcaseBuilderModal.tsx | ProblemControllerTest.java, testcase-builder.spec.ts | Transaction Integrity, Sample vs Hidden Testcase Validation, Input Sanitization | High
27 | Admin Contest Management & Soft Delete | Admin Dashboard | Admin | Admin panel to manage contests, edit problems, set scoring rules, soft delete/restore, and scope fallback. | Nguyễn Duy Phương | DE190416 | Done | iter4 | c05c6e5, 5ccd747, 2d600de, 0520a14 | AdminContestController, ContestService (POST/PUT/DELETE /api/v1/admin/contests) | AdminContestListPage.tsx, ContestEditorModal.tsx | ContestControllerTest.java, admin-contests.spec.ts | Soft Delete Safety Checks (Zero Submissions Guard), Scope Fallback to PRACTICE, Pagination | Critical
28 | Problem Versioning & Testcase History Audit | Admin Dashboard | Admin | Version control for problem descriptions, constraints, and testcase histories; version diffing and rollback protection. | Nguyễn Văn Quang | DE190094 | Done | iter4 | 3c4c480, 47b31bf, e74812f | ProblemAdminController, ProblemService (GET/POST /api/v1/admin/problems/{id}/history) | ProblemHistoryDrawer.tsx, VersionDiffViewer.tsx | ProblemControllerTest.java, problem-versioning.spec.ts | Immutable Audit Log Entries, JSON Diffing, Rollback Transaction Protection | High
29 | Idempotent Contest Finalization & Awards Engine | Competitive Programming | System | Background scheduler (@Scheduled) for contest finalization, winner entity creation, unique transaction idempotency checks. | Nguyễn Duy Phương | DE190416 | Done | iter4 | c270241, c762940, b5217f1 | ContestFinalizationScheduler, AwardService (PATCH /api/v1/admin/contests/{id}/finalize) | WinnerModal.tsx, AwardBadge.tsx | ContestFinalizationTest.java, award-service.spec.ts | Idempotency Reference Key Enforcement, Scheduled Cron Execution, DB Transaction Isolation | Critical
30 | Global Leaderboard | Public Pages | Guest | Show global student rankings with support for guest users. | Trịnh Hoàng Thiên Bảo | DE190023 | Done | iter4 | e1bdfc5, 76e9fa8 | PublicLeaderboardController, UserService (GET /api/v1/public/leaderboard) | GlobalLeaderboardPage.tsx, StudentRankTable.tsx | UserServiceTest.java, global-standings.spec.ts | Public Read Cache (TTL 60s Redis), Profile Anonymization, Guest Access Support | Medium

## Iter1
Iteration Tracking - Iteration 1 Detailed Execution Matrix
Scope committed and verified for Iteration 1 with exact SRS/SDS mapping and test evidence.
# | Screen / Function | Feature Area | Screen/Function Description | In Charge | MSSV | Status | SRS Code | SDS Code | Git Commit Hash | API Endpoints & Controllers | Frontend Components | Automated Tests | NFR / Security & AI Integration | Complexity
1 | PostgreSQL Database Schema & Relational Model | Database & Architecture | Designed PostgreSQL relational schemas, JPA Entity models, indexes, transaction isolations, and DB seed scripts. | Nguyễn Văn Quang | DE190094 | Done | II.9.1 | III.9.1 | init.sql, entity mappings | Database Schema, JPA Entities (User, Course, Problem, Contest, Transaction) | N/A (Database Core) | EntityUnitTest.java, DatabaseIntegrationTest.java | PostgreSQL 15, B-Tree Indexes, Referential Integrity, Isolation.REPEATABLE_READ | Critical
2 | Login Page | Authentication | Sign in using standard credentials or Google OAuth2 with secure HttpOnly cookies. | Võ Ngọc Thanh | DE190293 | Done | II.1.1 | III.1.1 | 716d9e4, 85d5b38 | AuthenticationController, AuthenticationService (POST /api/v1/auth/login) | LoginPage.tsx, LoginForm.tsx, authStore.ts | AuthenticationServiceTest.java, auth-login.spec.ts | JWT Bearer Cookies, BCrypt (cost 12), Brute-force rate limit | Critical
3 | Register Page | Authentication | Sign up for student accounts and create initial profiles with email verification. | Võ Ngọc Thanh | DE190293 | Done | II.1.2 | III.1.2 | 673d441, 716d9e4 | AuthenticationController, UserService (POST /api/v1/auth/register) | RegisterPage.tsx, RegisterForm.tsx | AuthenticationServiceTest.java, auth-register.spec.ts | Email Token Verification, Input XSS Sanitization | High
4 | User Profile Page | Profile | View/edit personal details, change passwords, avatar upload, and update emails. | Võ Ngọc Thanh | DE190293 | Done | II.1.3 | III.1.3 | 63f1c99, 7c0afd4 | UserController, UserService (GET/PUT /api/v1/users/profile) | ProfilePage.tsx, AvatarUploader.tsx | UserServiceTest.java, student-profile.spec.ts | Cloudinary CDN Avatar Upload, Optimistic Locking (@Version) | Medium
5 | User Management Panel | Admin Dashboard | Admin interface to view users, search, and lock/unlock accounts dynamically. | Trịnh Hoàng Thiên Bảo | DE190023 | Done | II.6.1 | III.6.1 | 76e9fa8, 0520a14 | AdminUserController, AdminDashboardService (GET/PATCH /api/v1/admin/users) | AdminUserTable.tsx, UserFilterBar.tsx | AdminDashboardServiceTest.java, admin-users.spec.ts | RBAC (@PreAuthorize('hasRole("ADMIN")')), Soft Delete, Dynamic JPA Specs | High
6 | Instructor Applications | Admin Dashboard | Review applicant CVs, check credentials, approve/reject with AI CV summary. | Trịnh Hoàng Thiên Bảo | DE190023 | Done | II.6.2 | III.6.2 | 76e9fa8, c4c2b70 | InstructorApplicationController (POST /api/v1/admin/applications/{id}/approve) | ApplicantReviewModal.tsx, AISummaryBadge.tsx | InstructorApplicationServiceTest.java, instructor-approval.spec.ts | AI CV Summary (PDF Parsing + LLM), Async ApplicationApprovedEvent | High

## Iter2
Iteration Tracking - Iteration 2 Detailed Execution Matrix
Scope committed and verified for Iteration 2 with exact SRS/SDS mapping and test evidence.
# | Screen / Function | Feature Area | Screen/Function Description | In Charge | MSSV | Status | SRS Code | SDS Code | Git Commit Hash | API Endpoints & Controllers | Frontend Components | Automated Tests | NFR / Security & AI Integration | Complexity
7 | Problems Directory | Online Judge | View paginated list of public practice coding challenges with filters. | Võ Ngọc Thanh | DE190293 | Done | II.2.1 | III.2.1 | 0a67378, 7c0afd4 | ProblemController, ProblemService (GET /api/v1/problems) | ProblemListPage.tsx, ProblemFilter.tsx | ProblemControllerTest.java, catalog-search.spec.ts | Redis Tag Caching, Full-Text Search Index, Prepared Statement SQL Protection | Medium
8 | Solve Problem Page | Online Judge | Integrated workspace to code solutions, run tests, and check results (Judge0). | Võ Ngọc Thanh | DE190293 | Done | II.2.2 | III.2.2 | 998b82d, 4ce8206 | SubmissionController, Judge0Service (POST /api/v1/submissions) | ProblemSolvePage.tsx, MonacoEditor.tsx, TestResultPanel.tsx | Judge0ServiceTest.java, problem-solving.spec.ts | Docker Sandbox Execution via Judge0 API, Sub-second Polling, Memory/Time limits | Critical
9 | Course Directory | Course Learning | Browse and filter programming courses with a responsive grid layout. | Võ Ngọc Thanh | DE190293 | Done | II.3.1 | III.3.1 | 74ba98a, 716d9e4 | CourseController, CourseService (GET /api/v1/courses) | CourseCatalogPage.tsx, CourseCard.tsx | CourseServiceTest.java, course-catalog.spec.ts | Responsive Grid, Dynamic Filtering, Lazy-loaded Image CDN | Medium
10 | Course Details | Course Learning | Deep view of course curriculum, chapters, video player, and student reviews. | Hồ Sĩ Tấn | DE190307 | Done | II.3.2 | III.3.2 | 74ba98a, c4c2b70 | CourseController, CourseService (GET /api/v1/courses/{id}) | CourseDetailPage.tsx, VideoPlayer.tsx | CourseServiceTest.java, course-details.spec.ts | Cloudinary HLS Video Streaming, Enrolled Status Check, Safe Markdown Render | High
11 | Shopping Cart & Checkout | Course Learning | Add courses to cart, view wallet balance, and purchase courses safely. | Võ Ngọc Thanh | DE190293 | Done | II.3.3 | III.3.3 | 283ca52, 12f8dc0 | PaymentController, PaymentService, WalletService (POST /api/v1/checkout) | CartPage.tsx, CheckoutModal.tsx | PaymentServiceTest.java, course-checkout.spec.ts | Idempotent Payments, Isolation.REPEATABLE_READ DB Transactions, Audit Logs | Critical
12 | Course Moderation | Admin Dashboard | AI-powered moderation checking course videos via FFmpeg transcriptions. | Trịnh Hoàng Thiên Bảo | DE190023 | Done | II.6.3 | III.6.3 | c4c2b70, 76e9fa8 | CourseModerationController, CourseModerationService | ModerationQueuePage.tsx, VideoTranscriptViewer.tsx | CourseModerationServiceTest.java, course-moderation.spec.ts | FFmpeg Audio Extraction + Whisper AI Transcription + LLM Content Safety | Critical
13 | Instructor Revenue Analytics Dashboard | Instructor Dashboard | Real database revenue analytics, lifetime gross/net calculations, 6/12-month timeframe toggles, dynamic SVG chart grid points. | Nguyễn Văn Quang | DE190094 | Done | II.5.4 | III.5.4 | 6da05b2, 285bdb8, c4124a4 | InstructorRevenueController, RevenueService (GET /api/v1/instructor/revenue) | InstructorRevenueDashboard.tsx, RevenueChart.tsx | RevenueServiceTest.java, instructor-revenue.spec.ts | Realtime DB Revenue Aggregation, Zero-value Month Auto-padding, Dynamic SVG Grid | High
14 | Platform Financial Reports & Financial Metrics | Admin Dashboard | Platform-wide gross/net financial metrics, payout logs, transaction audit trail, optimized range queries. | Nguyễn Văn Quang | DE190094 | Done | II.6.4 | III.6.4 | 3b2e60f, 33f57a6, 550369a | FinancialReportController, DashboardService (GET /api/v1/admin/reports) | FinancialDashboardPage.tsx, RevenueChart.tsx | DashboardServiceTest.java, financial-reports.spec.ts | Gross/Net Revenue Calculations, CSV Export, Indexed Range Queries | High
15 | Contest Directory & Spotlight Banner | Competitive Programming | View active/upcoming/ended contest list, status filter, dynamic spotlight banner, password registration lock. | Nguyễn Duy Phương | DE190416 | Done | II.7.1 | III.7.1 | 12ad54d, e60d4c8, 0349342 | ContestController, ContestService (GET /api/v1/contests) | ContestListPage.tsx, SpotlightBanner.tsx, PasswordModal.tsx | ContestControllerTest.java, contest-arena.spec.ts | Password Locking (Argon2id), UTC ISO Time Synchronization, Registration Guard | High

## Iter3
Iteration Tracking - Iteration 3 Detailed Execution Matrix
Scope committed and verified for Iteration 3 with exact SRS/SDS mapping and test evidence.
# | Screen / Function | Feature Area | Screen/Function Description | In Charge | MSSV | Status | SRS Code | SDS Code | Git Commit Hash | API Endpoints & Controllers | Frontend Components | Automated Tests | NFR / Security & AI Integration | Complexity
16 | AI Tutor Panel | AI Assistance | Side panel in problem solver providing custom feedback and hint guidelines. | Võ Ngọc Thanh | DE190293 | Done | II.4.1 | III.4.1 | 86bb8a8, 8644a3d | AiAssistanceController, AiEvaluationService (POST /api/v1/ai/tutor/hint) | AiTutorDrawer.tsx, HintBubble.tsx | AiEvaluationServiceTest.java, ai-tutor.spec.ts | Prompt Injection Shielding, Token Rate Limiting, Strict System Persona | High
17 | AI Algorithm Visualizer | AI Assistance | Visualizes code execution flows with adjustable speed and cached responses. | Võ Ngọc Thanh | DE190293 | Done | II.4.2 | III.4.2 | 8644a3d, 85d5b38 | AiAssistanceController, AiEvaluationService (POST /api/v1/ai/visualize) | AlgorithmVisualizerCanvas.tsx, ExecutionSlider.tsx | AiEvaluationServiceTest.java, algorithm-visualizer.spec.ts | Redis Execution Trace Cache, Client-side Canvas Step Animation | High
18 | Lesson Q&A Comments | Course Learning | Ask questions under specific lessons and reply to other students. | Võ Ngọc Thanh | DE190293 | Done | II.3.4 | III.3.4 | 74ba98a, 716d9e4 | CommentController, CommentService (POST /api/v1/lessons/{id}/comments) | LessonCommentSection.tsx, CommentThread.tsx | CourseServiceTest.java, lesson-comments.spec.ts | Tree Comment Hierarchy, Profanity Filter, Stored XSS Protection | Medium
19 | Create/Edit Course | Instructor Dashboard | Create chapters, lectures, upload lecture videos to Cloudinary, and save drafts. | Hồ Sĩ Tấn | DE190307 | Done | II.5.1 | III.5.1 | 046deeb, c4c2b70 | InstructorCourseController, InstructorCourseService (POST /api/v1/instructor/courses) | CourseBuilderPage.tsx, LectureUploader.tsx | InstructorCourseServiceTest.java, course-builder.spec.ts | Cloudinary Signed Upload Signatures, Draft Autosave, Cascading Soft Delete | Critical
20 | Monaco Code Editor Integration | Instructor Dashboard | Integrated editor in coding exercises with syntax highlighting. | Hồ Sĩ Tấn | DE190307 | Done | II.5.2 | III.5.2 | 998b82d, c4c2b70 | ExerciseController, InstructorCourseService | MonacoExerciseEditor.tsx, LanguageSelector.tsx | InstructorCourseServiceTest.java, monaco-editor.spec.ts | Multi-language Syntax (Java, C++, Python), Client Code Linting, Local Backup | High
21 | Auto Testcase Generator | Instructor Dashboard | Auto-generate input/output testcases for instructor exercises. | Hồ Sĩ Tấn | DE190307 | Done | II.5.3 | III.5.3 | c4c2b70, 8644a3d | TestcaseGeneratorController, AiEvaluationService | TestcaseGeneratorModal.tsx, InputOutputGrid.tsx | AiEvaluationServiceTest.java, testcase-generator.spec.ts | LLM Boundary Value Analysis, Edge Case Hardening, Docker Reference Exec | High
22 | Contest Arena Problem Workspace | Competitive Programming | Arena interface with live time countdown, anti-cheat mode (no hints), problem attempts persistence. | Nguyễn Duy Phương | DE190416 | Done | II.7.2 | III.7.2 | 72086d9, de3576f, e69b5e7 | ContestController, ContestSubmissionRepository (POST /api/v1/contests/{id}/submissions) | ContestProblemSolve.tsx, MonacoEditor.tsx, ContestHeader.tsx | ContestControllerTest.java, problem-solving.spec.ts | Realtime WebSocket / SSE Feedback, Attempt History DB Persistence, Anti-cheat | Critical
23 | ICPC Live Scoreboard & Ranking Stream | Competitive Programming | Real-time ICPC penalty scoring engine (Redis ZSET + SSE Stream + JSON Snapshot DB Fallback Recovery). | Nguyễn Duy Phương | DE190416 | Done | II.7.3 | III.7.3 | 774ca94, ca5496d, 7bc07b4, dfd2923 | ContestScoreboardController, RankingService (GET /api/v1/contests/{id}/stream) | LiveScoreboardPage.tsx, LeaderboardTable.tsx | ContestControllerTest.java, scoreboard.spec.ts | Redis Sorted Set (ZSET) Engine, SSE Live Stream, Snapshot JSON DB Fallback | Critical
24 | Dynamic Contest Status Evaluation Engine | Competitive Programming | Runtime evaluation of UPCOMING / ONGOING / ENDED states based on Instant.now(), eliminating static DB enum sync bugs. | Nguyễn Duy Phương | DE190416 | Done | II.7.4 | III.7.4 | 2e3576f, 2c7ae5d, 8924b41, 9fab4b0 | ContestService, ContestRepository (JPQL Dynamic Queries) | ContestBadge.tsx, StatusFilterBar.tsx | ContestServiceTest.java, integration-tests.spec.ts | Zero DB Static Column Overhead, UTC Timestamp Precision, Dynamic Status JPQL | High
25 | Admin System Overview & Database Metrics | Admin Dashboard | Real-time DB health monitoring, total active user/course/submission counters, platform system statistics aggregation. | Nguyễn Văn Quang | DE190094 | Done | II.6.6 | III.6.6 | 6b8b6f0, 536da33, 8d09c30 | AdminDashboardController, SystemMetricsService (GET /api/v1/admin/stats) | AdminDashboardPage.tsx, StatCard.tsx | DashboardServiceTest.java, admin-stats.spec.ts | Sub-second Query Execution, Cached Stat Aggregation (TTL 30s), DB Health Monitoring | Medium
26 | Admin Problem Management & Testcase Builder | Admin Dashboard | Comprehensive admin problem CRUD, input/output testcase builder, sample vs hidden testcase management. | Nguyễn Văn Quang | DE190094 | Done | II.6.7 | III.6.7 | 9c39a98, 434df81, 0cf9d01 | AdminProblemController, TestcaseService (POST /api/v1/admin/problems) | AdminProblemEditor.tsx, TestcaseBuilderModal.tsx | ProblemControllerTest.java, testcase-builder.spec.ts | Transaction Integrity, Sample vs Hidden Testcase Validation, Input Sanitization | High

## Iter4
Iteration Tracking - Iteration 4 Detailed Execution Matrix
Scope committed and verified for Iteration 4 with exact SRS/SDS mapping and test evidence.
# | Screen / Function | Feature Area | Screen/Function Description | In Charge | MSSV | Status | SRS Code | SDS Code | Git Commit Hash | API Endpoints & Controllers | Frontend Components | Automated Tests | NFR / Security & AI Integration | Complexity
27 | Admin Contest Management & Soft Delete | Admin Dashboard | Admin panel to manage contests, edit problems, set scoring rules, soft delete/restore, and scope fallback. | Nguyễn Duy Phương | DE190416 | Done | II.7.5 | III.7.5 | c05c6e5, 5ccd747, 2d600de, 0520a14 | AdminContestController, ContestService (POST/PUT/DELETE /api/v1/admin/contests) | AdminContestListPage.tsx, ContestEditorModal.tsx | ContestControllerTest.java, admin-contests.spec.ts | Soft Delete Safety Checks (Zero Submissions Guard), Scope Fallback to PRACTICE, Pagination | Critical
28 | Problem Versioning & Testcase History Audit | Admin Dashboard | Version control for problem descriptions, constraints, and testcase histories; version diffing and rollback protection. | Nguyễn Văn Quang | DE190094 | Done | II.6.5 | III.6.5 | 3c4c480, 47b31bf, e74812f | ProblemAdminController, ProblemService (GET/POST /api/v1/admin/problems/{id}/history) | ProblemHistoryDrawer.tsx, VersionDiffViewer.tsx | ProblemControllerTest.java, problem-versioning.spec.ts | Immutable Audit Log Entries, JSON Diffing, Rollback Transaction Protection | High
29 | Idempotent Contest Finalization & Awards Engine | Competitive Programming | Background scheduler (@Scheduled) for contest finalization, winner entity creation, unique transaction idempotency checks. | Nguyễn Duy Phương | DE190416 | Done | II.7.6 | III.7.6 | c270241, c762940, b5217f1 | ContestFinalizationScheduler, AwardService (PATCH /api/v1/admin/contests/{id}/finalize) | WinnerModal.tsx, AwardBadge.tsx | ContestFinalizationTest.java, award-service.spec.ts | Idempotency Reference Key Enforcement, Scheduled Cron Execution, DB Transaction Isolation | Critical
30 | Global Leaderboard | Public Pages | Show global student rankings with support for guest users. | Trịnh Hoàng Thiên Bảo | DE190023 | Done | II.8.1 | III.8.1 | e1bdfc5, 76e9fa8 | PublicLeaderboardController, UserService (GET /api/v1/public/leaderboard) | GlobalLeaderboardPage.tsx, StudentRankTable.tsx | UserServiceTest.java, global-standings.spec.ts | Public Read Cache (TTL 60s Redis), Profile Anonymization, Guest Access Support | Medium